## Cover
ETF
BPS Post Mortem
2004-04-16

## Summary
ETF
BPS Post Mortem
Evaluation Instance
| Benchmarking Date | Evaluation / Pre-RFS | RFS | BPS
Project Area
1 | Business Case/ROI | 1.6667 | 1.6667 | 2
2 | Sponsorship | 2.1429 | 2.7143 | 3.1429
3 | Scope | 2.25 | 3.625 | 3.75
4 | Approach | 3.6 | 4 | 4.2
5 | Resource Management | 2.2 | 2.5 | 2.8
6 | Communication Management | 1.6667 | 2.1111 | 2.7778
7 | Issue Management | N/A | N/A | 4
8 | Risk Management | N/A | N/A | 3.8
9 | Quality Assurance | N/A | N/A | 3.8333
10 | Work Management | NA | N/A | 3.7778
11 | Technology | 2.375 | 2.5 | 2.75
| Total | 2.2716 | 2.731 | 3.3483
Key Recommendations
1
2
3
SCORING 1 UTILIZED (0 - 2) Best practices utilized by organization 2 3 RECOGNIZED (2.01 - 3.50) Best practice recognized but not utilized by organization 4 5 NOT RECOGNIZED (3.51 - 5.00) Best practice not recognized by organization

## Detail
ETF Project Phases
Large Project Best Practices |  | Evaluation / Pre-RFS | RFS | BPS | Assessment | Evidence | Lessons Learned/Go Forward
1 | Business Case/ROI | 1.6667 | 1.6667 | 2
| Why is project being considered? | 3 | 2 | 2 | Current system no longer supports the needs of the business. Changes are costly and timely to conduct. System lack bare essential functionality. | Basic functionality is lacking which has compromised the quality of service. | At a high level, the business case appears to be reasonable. The New Payment System provides cost savings, reduction in workloads, faster processing, and increase customer satisfaction. It is unclear whether the detailed requirements/designs have been cost justified. As the project is re-scoped, care should be given to ensuring each requirement is necessary.
| Is project viable? Can it be achieved? | 1 | 1 | 2 | Project represents a reasonable solution to the need to improve efficiency, service and replace obsolete systems. Project technical direction is also consistent with modern systems development practices. The current scope is large and of high risk requiring adequate management, skills and resources. | All existing documentation
| Business case has been communicated | 1 | 2 | 2 | Business case communicated throughout project. Clearly understood due to same team in-place from inception. | The New Payment System is a high priority for the department and is consistent with the Strategic Business Plan vision and goals.
2 | Sponsorship | 2.1429 | 2.7143 | 3.1429
| Appropriate sponsor is identified and supports project | 3 | 4 | 4 | Single sponsor was prevalent at the conception of the project. Over time split sponsorship between Business and IT caused confusion with administration and facilitation. | Effective transition of sponsors was needed with a project of this caliber. | Assign a single, experienced sponsor with enough availability • Overall responsibility/authority for driving both functional and technical decisions. This will be especially important for ETF since common/traditional/historical challenges appear to exist between IS and the business that will require effective issue resolution at a project level. • Single point of contact for issue escalation/resolution • Experience that allows the sponsor to assess true project progress • Able to invest adequate time on the project to proactively ensure success
| Sponsor has authority to resolve issues | 3 | 4 | 4 | As issues were escalated, two sponsors existed which did not allow for effective mitigation. | Business issues were managed by business sponsor and IT issues were managed by IT sponsor. Lack of collaboration between business units to ensure consistency.
| Sponsor has control over project resources | 3 | 3 | 3 | Sponsor had appropriate control over Functional team. Sponsors did not invoke proper control over all IT staff. | Technical team members appear to have disapproved of decision-making with regard to vendor selection and various technical decisions, which caused animosity and lack of team member buy-in
| Project funding is adequate to support project scope | 2 | 2 | 2 | Funding appears to have been appropriate. Significant scope could have been delivered using a target costing approach with this level of funding, possibly deferring lower priority items. | A budget of $7.7M+ is sufficient to realize a significant system on the scale of BPS.
| End user stakeholders buy-in to project | 1 | 2 | 2 | Overall end-users understood scope and objectives. | Team member support diminished after a year had past and they had nothing to show for it. Redundant efforts in conducting process flows and use cases twice.
| Management team stakeholders buy-in to project | 1 | 1 | 3 | Management fully understood the need to upgrade system. | Customer service was affected. The legacy system overhead was experienced with increased expenditures (maintenance) and the increase in manual processes.
| Technical team stakeholders buy-in to project | 2 | 3 | 4 | As project progressed, technical team lost confidence in management decisions. | Technical team expressed concern with vendor choice when they were unable to prove they contained the experience and skill set needed to conduct project.
3 | Scope | 2.25 | 3.625 | 3.75
| Vision clearly defined and understood | 1 | 4 | 4 | Vision clearly defined during project conception. New Payment System Analysis suggested automation which added significantly to the original scope. | Solution Confirmation, Analysis of NPS Final Report, EDD, RFS | ETF had a manageable scope and then it grew to a point that it was no longer manageable if approached as a single phase project. Going forward, Scope Management will be needed to determine whether or not a proposed change is viable or shall be shelved for future development.
| Project charter exists with clearly defined scope | 2 | 3 | 4 | Project Charter not available, assumed Solution Confirmation documentation fulfilled charter requirements. | Solution Confirmation
| Core requirements are identified and documented | 2 | 3 | 3 | Core requirements captured, but as the project evolved no single source documenting existed. Core requirements found in EDD, Process Flows, and Use Cases. | Solution Confirmation, Analysis of NPS Final Report, EDD, RFS
| Main constraints are identified and documented | 3 | 3 | 3 | Concern of budget, resources, time, and scope are all documented, but the imbalance was not addressed. No formal process can be found that identified the process that explained how to mitigate tradeoffs among budget, resource, and time. | Preliminary project risks were identified but were not managed.
| Scope is approved and signed off | 3 | 4 | 4 | Sign-off and clear understanding of scope did was lacking. | No evidence of sign-off or formal agreement of scope.
| Project baseline is established | 2 | 4 | 4 | Limited evidence that a baseline was ever established. | Baselines were never established as new project plans were developed with each change that was applied to project.
| Proper resources are available to support the scope | 2 | 4 | 4 | As project scope increased the increase in resource demand was not recognized in the project plan. | Vendor did not demonstrate the project management, technical, or methodology skills and experience that were needed.
| Scope Management process has been developed and followed | 3 | 4 | 4 | Process identified, but not followed. | BPS Scope Assessment, Feb. 2003 identified scope change but the impact and risk were not appropriately applied.
4 | Approach | 3.6 | 4 | 4.2
| Project divided into manageable phases | 2 | 4 | 5 | No phasing is evident. Big bang approach used. | Overall phasing and Iterations within phases did not exist in planning. Considered automating and integrating with all subsystems. | Best practices demonstrate that Use Cases and Business Requirements are dependencies that the Architecture Framework will use in its build. The RUP framework needs to be fully understood by all team members involved to demonstrate their competence with the methodology for it to be effective. RUP is a very involved methodology with many tools. It is suggested that ETF only apply the methods and tools that will positively impact the project lifecycle structure.
| Alternate solutions have been considered (package vs. custom) | 4 | 4 | 4 | Package solution was not considered. Given the perceived scope at the time of the RFS, it is believed that package solution was not available. | Analysis of New Payment System Final Report did not have package solution as a alternative approach.
| Project Methodology - Rational Unified Process (RUP) | 4 | 4 | 4 | RUP methodology was recognized but not followed. Use Cases were never realized, which hampered the design effort and the build of prototypes to prove framework early in Elaboration. Framework was built in parallel to Use Cases which forced broad assumptions to be made. This led to the framework becoming too complicated to implement. | Waterfall approach is evident in project plans. Use Cases were too detailed and never realized (i.e. design, prototype, re-evaluated for improvement).
| Organization experienced in project methodology | 4 | 4 | 4 | ETF did not have the skills necessary to use RUP. | Team member had never conducted Use Case development before BPS. Intense and limited training was the only experience some team members encountered before BPS involvement.
| Project team experienced in project methodology | 4 | 4 | 4 | Covansys, Maximus did not have the technical experience to facilitate the project using RUP. | Vendor sat in on RUP and Use Case training with ETF staff.
5 | Resource Management | 2.2 | 2.5 | 2.8
| Project Team Organizational Structure defined | 2 | 2 | 2 | Team structure was clearly identified and documented. | Solution Confirmation, BPS Project Organizational Chart | Convansys did not bring "A-team" as implied in the selection process. Resources issued did not have the business or technical competencies needed to facilitate BPS. Maximus did not properly monitor the project. ETF did not hold vendors accountable for missed deliveries and milestones.
| Team Roles & Expectations defined | 1 | 1 | 1 | Adequate definition surrounding roles and responsibilities. | Solution Confirmation, BPS Project Organizational Chart
| Project manager available and committed | 1 | 1 | 1 | Functional Team, IT, and Vendor PM resources available and committed.
| Functional Team available and committed | 2 | 3 | 4 | Functional Team readily involved in process flow and use case development. Lack of backflow and ACT11 made resource availability over-allocated. | Underestimated functional time and backfill needed (i.e. ACT 11 which resulted in backlog of work)
| Technical Team competencies match requirements | 4 | 4 | 4 | Vendor technical staff did not fit the project profile needed for the BPS project. | Vendor team members did not possess Java, J2EE, or RUP experience
| Training provided to team members for project skills required | 3 | 3 | 3 | Resources were not experienced enough to conduct use case analysis and build technical framework. | Training was provided in short, intense intervals. Didn't apply skills immediately which deteriorated over time.
| Third Party involvement managed | 2 | 3 | 4 | Project Monitor failed. ETF failed to hold vendors accountable for missed deliverables. Cause may have been that ETF had never experienced this type of project before. Trust was given to vendors to conduct job based on contract agreement. | Project Monitor has little evidence to support that it made good on its contract. Outsource provided programs that did not compile. BPS team demonstrated their lack of Use Case knowledge by only providing a 50% completion after nine months.
| Level of team work, enthusiasm, and morale | 2 | 3 | 4 | Project initiation provided excitement that reoccurring business issues would be resolved. As project evolved the camaraderie dwindled to due the decisions made and the lack of results to show for the effort put into the project. | Conflict and tension existed between IT and Functional teams during BPS.
| Subject Matter Experts available for knowledge transfer | 2 | 2 | 2 | Knowledgeable function team members involved in process flow sessions and use case meetings. | Functional team members assigned to all use cases sessions and QA process
| Resource commitments across other projects are understood | 3 | 3 | 3 | ETF team members were over allocated. Presumption was that vendors were hired to provide project resources, benefit experience, Use Case experience, and RUP experience. ETF expected to lean on vendors for guidance. | Vendor failed to recognize in project plans ACT11 project efforts. ETF resources were over-allocated.
6 | Communication Management | 1.6667 | 2.1111 | 2.7778
| Team members clearly understood their role | 1 | 3 | 3 | Roles were clearly identified upfront. As project gained scope and size, team members found their role and contributions to be frustrating. | Solution Confirmation clearly identifies roles and responsibilities. | Roles and responsibilities need to be understood at all levels of the project (i.e. sponsor, stakeholders, PM's, business analysts, etc.). A communication plan needs to be developed that clearly states project roles, the responsibilities associated with the role, and the resources assigned. Project Plans need to be clearly communicated so team members know when something is expected of them. Regularly scheduled meetings (i.e. team, steering committee) are critical so that all project members are aware of the status at all times. Project documentation is centrally located and readily available to all team members (i.e. risk list, issues list, meeting minutes, specification documents, etc.)
| Project expectations and deliverables understood by team | 2 | 2 | 4 | Replacing the flat file structure with the New Payment System was understood by all resources involved. As the BPS scope grew, team members found the endeavor to be overwhelming | Solution Confirmation, RFS
| Project kickoff conducted with sponsors and team | 1 | 1 | 1 | Project kickoff conducted | Meeting agenda: users/bpsaudit/bps/project phases/01inception/01milestones/01project planning/project agenda kickoff.doc
| Ongoing team meetings are held | 1 | 2 | 2 | Communication was communicated regularly via team status meetings; however, issues were rarely addressed nor were action plan developed to provide resolution | Documented issue and risk plans, but the status of mitigation indicates process was absent.
| Regular status reports are completed | 2 | 2 | 2 | Yes but weak status reports and misleading | Status Reports: users/bpsaudit/bps/project management office/time and status reporting
| Information is openly shared by team members | 2 | 3 | 3 | Environment may not have allowed for unbiased or open communication. | Team members raised concern regarding risk and issues, but were told not to be concerned, "Trust Covansys."
| Steering committee meets regular and is actively involved | 2 | 2 | 4 | Steering committee meetings were mislead and project status was misrepresented | ETF steering committee lead to believe project was under control
| Project information is consistently communicated at all project levels | 2 | 2 | 4 | Status meetings were held regularly, but awareness and results lacked. | Communication up management chain was misleading in that the perception was that the project was on-target.
| A central project library exists and is accessible by all team members | 2 | 2 | 2 | Yes | LAN documentation directory
7 | Issue Management | N/A | N/A | 4
| Issue management process is in place and utilized | N/A | N/A | 4 | The documentation and strategy was well defined. The proper execution to find resolution was completely missing. | Policy and procedure: users/bpsaudit/bps/project management office. Issues were documented but not assigned or resolved. | Issue management is more than documentation. It requires that team members be accountable for executing action plans to bring about resolution when issued are identified.
| Escalation process to appropriate stakeholders is in place | N/A | N/A | 4 | Escalation to stakeholders is evident. Concern exists with the process after PM's received issues. | Issues were well documented and communicated at the monthly steering committee meetings, but meeting minutes demonstrate nothing was resolved from one monthly meeting to the next.
| Resources are available to make critical decisions | N/A | N/A | 4 | The escalation of issues and resolution by key stakeholders and sponsors was not evident. | Lack of issue resolution
| Issues are resolved in a timely fashion | N/A | N/A | 4 | Complex issues documented as being resolved with a 30 day window | Lack of documentation suggests issues were not resolved in a timely fashion
8 | Risk Management | N/A | N/A | 3.8
| Risk management process is in place and utilized | N/A | N/A | 4 | Risk management process communicated to ETF steering committee. Real risks not noted very well. | Documentation suggests risks were tracked but not effectively addressed. | A formal process is needed to manage risk throughout the project lifecycle. Utilizing tools is a valuable way to record and track the mitigation of project risks. Starting with the inception of the project, known risks need to be identified and understood so the decision can e made whether to avoid the risk or accept the risk. Risks can be related to scope, technology, resource, time, and/or budget. It is important to prioritize the risks based on impact and probability. Once the risks are understood, assigning the risk to members of the team provide accountability that risk are being addressed. The risk process is reoccurring throughout the project. As risks are identified they need to be added to the master list. The list then needs to be re-prioritized as to understand the high priority items and assurance that they are being addressed.
| Risks have been identified | N/A | N/A | 3 | Twenty seven risk identified during project inception conducted by Maximus. ETF involved in the definition of risks, identify responsible resource, and mitigation actions. | Conducted original project risk assessment April/May 2002
| Qualitative analysis conducted to define impact and probability | N/A | N/A | 4 | Based on initial risk assessment, project risk impact and probability was determined. | Conducted original project risk assessment April/May 2002. Documentation suggests risks were tracked but not effectively addressed.
| Mitigation plan is in place and utilized | N/A | N/A | 4 | There is no evidence of mitigation plans other than scheduling more meetings | There is no evidence of mitigation plans other than scheduling more meetings
| Contingency plan developed in the event objectives not met | N/A | N/A | 4 | There is not evidence of contingency plans until just prior to BPS being cancelled (i.e. jClarity). | Meeting minutes suggest that Covansys tried to salvage project by offering the jClarity product as a solution to the failed custom approach.
|  | N/A | N/A
9 | Quality Assurance | N/A | N/A | 3.8333
| Quality management process is in place and utilized | NA | NA | 4 | Quality Assurance very low. The project monitor roll failed to inform the steering committee of major risks and justify delinquent deliverables. Deliverables were rewarded with payment rather than objective critique (i.e. use cases were incomplete, framework was over engineered and did not comply with use case development, delinquency in deliverables continued to be detriment to the project plan) | ETF management was reactive to many situations and issues. ETF resources not available full-time. BPS tasks were shared with day-to-day responsibilities. | Quality Assurance provides a clear understanding of how project deliverables are to assessed and approved. This effort is conducted throughout the project lifecycle and ensures quality to all deliverables (i.e. vision, use cases, business rules, risk management, issue resolution, design, development, testing, deployment plan, etc.)
| Method exists to match client expectations with quality of project deliverables | NA | NA | 4
| Appropriate levels testing and user sign-off | NA | NA | 3
| Service level targets are defined and measurable | NA | NA | 4
| Service level targets are defined and measurable | NA | NA | 4
| Milestones are reviewed against baseline, plan adjusted as needed | NA | NA | 4
10 | Work Management | NA | N/A | 3.7778
| Project plan outlines tasks at team member level | N/A | N/A | 4 | Project plans were not readily available. The plan itself did not outline team member tasks and it losely communicated milestones and deliverabels. The project plan did not account for dependencies. | Project plans were continually requested by ETF, but vendors failed to provide. The plan did not account for project and resource dependencies (i.e. vacations, Act 11). As changes occurred and deliverabels were missed, the project plan did not properly keep the project team, stakeholders, and sponsor(s) informed. | Work plans need to be clearly communicated so every team member understands their task at-hand and when it is to be delivered. Project schedules outline the interdependencies of all the concurrent efforts. Using tools to establish a clear understanding of the project status is critical. Estimates for task efforts need to involve the individuals who are executing the tasks; thus, to gain an objective view and appreciation of how long the task will take and provide confidence to the resource and giving credibility to the project plan.
| Project plan outlines expected deliverables | N/A | N/A | 3
| Project plan outlines milestones | N/A | N/A | 3
| Project plan includes dependencies | N/A | N/A | 4
| Confidence in estimate and schedule | N/A | N/A | 4
| Estimating assumptions understood and documented | N/A | N/A | 4
| Process in place to track actual vs. planned | N/A | N/A | 4
| Process in place to manage magnitude of plan vs. actual variances | N/A | N/A | 4
| Process in place to diagnose and resolve work plan deviations | N/A | N/A | 4
11 | Technology | 2.375 | 2.5 | 2.75
| Chosen technology is mature | 2 | 2 | 2 | Business perception that technology choices drove the project out of scope
| Chosen technology aligns with existing environment | 2 | 2 | 2 | ETF determined early on, during the internal project assessment, that all the UI interface front end development would be done in JAVA and integrate with back-end COBOL processing.
| Appropriate tools in place to support project | 3 | 3 | 3
| Development standards exist and followed | 2 | 2 | 2
| Internal IT team familiar with chosen technology | 2 | 3 | 3
| External team familiar with chosen technology | 4 | 4 | 4
| Technical vision consistent with organizational vision | 2 | 2 | 2
| Business requirements drive architecture design | 2 | 2 | 4
SCORING 1 UTILIZED (0 - 2) Best practices utilized by organization 2 3 RECOGNIZED (2.01 - 3.50) Best practice recognized but not utilized by organization 4 5 NOT RECOGNIZED (3.51 - 5.00) Best practice not recognized by organization
NOTES + Use columns (G - I) to handle each instance of QA performed. + Score each best practices against a project, using the scoring table at the left. + Add assessment and evidence notes in column J and K that support the score. + Add key lessons learned and recommendations in column L.