Final Report:

Evaluation of the

Benefit Payment System Project

Prepared for:

State of Wisconsin

Department of Employee Trust Funds

July 12, 2004

July 12, 2004

Ms. Joanne Cullen

Administrator, Department of Information Technology

Department of Employee Trust Funds

801 West Badger Road

Madison, WI 53702-0011

Dear Joanne,

Following is our final report summarizing the results of our evaluation of the Department of Employee Trust Funds’ (ETF) Benefit Payment System (BPS) Project.  The primary contents of our report are structured as follows:

Section I:	Executive Summary

Section II:	Project Post Mortem Analysis

Section III:	Go Forward Recommendations

Section IV:	Immediate Next Steps

Additionally, our final deliverable includes numerous appendices and other project work papers that were created during our six week evaluation project.  Many of these work papers will need to be revised going forward as ETF completes the suggested immediate next step project activities.

We would like to thank ETF for providing Virchow Krause & Co. (VK) with this opportunity to serve the Department.  We would also like to thank the many ETF employees and various other project participants who were involved in making this project a success.  Without their forthright participation in interviews, their assistance in helping us to identify and process the many binders and electronic directories of information from the former BPS project and their participation in various project working sessions, we could not have completed our evaluation during this short six week project.

Please feel free to contact me or any other VK project team member with any questions you may have regarding any of our project deliverables as you move ahead with your recovery effort.  We wish ETF great success in its’ BPS recovery project!

Sincerely,

Virchow Krause & Co., LLP

Bryan Majewski

Partner

Table of Contents

Section I: Executive Summary	4

Section II: Project Post Mortem Analysis	11

A. 	BPS Project	11

B. 	BPS Monitor	13

C. 	Department of Electronic Government	14

D. 	BPS Business Case	14

E. 	Development Approach, Use Cases and Technology Architecture	14

Section III: Go Forward Recommendations	18

A. 	Revised Implementation Strategy	18

B.  	Package Alternatives and Solution Overview	19

D. 	Custom Build Overview	26

E. 	Project Team Structure	28

F. 	Conversion Strategy	31

G. 	Technical Architecture	31

Section IV: Immediate Next Steps	32

A. 	Project Charter	32

B.	RFP	33

C.  	Skills and Impact Assessment	34

D.  	Reengineering	34

Appendix A:  Post Mortem	35

Appendix B:  Revised Implementation Details	36

Appendix C:  Vendor ProfileAppendix D:  Detailed Cost Model	39

Appendix E:  High Level Conversion Strategy	41

Appendix F: High Level Architecture and Technical Design	42

Appendix G:  Assumptions	45

# Section I: Executive Summary

Evaluation Project Background

Virchow Krause &Co., together with members of ETF, DET (formerly DEG), Covansys, MAXIMUS, Inc. and nVISIA, completed a six week evaluation of the BPS Project beginning on April 5, 2004 and ending on May 18, 2004.

The purpose of this evaluation was to:

- Briefly determine why the BPS project failed, focusing on identifying lessons learned

- Briefly evaluate the role of the monitoring vendor, focusing on identifying lessons learned

- Briefly evaluate the role of DEG, focusing on identifying lessons learned

- Assess the initial BPS business case

- Develop an approach for recovering the BPS project

- Recommend whether a monitoring vendor role is needed going forward

Other project objectives and key guidelines included:

- Providing ETF with an alternative for implementing a meaningful amount of the BPS scope within ETF’s remaining project budget

- Considering package software solution alternatives

- Excluding any ‘bells and whistles’, including web based self service functionality from the minimum scope solution

Post Mortem Findings/Lessons Learned

- BPS Project inadequate

Based upon our brief assessment, following are the major reasons why the BPS project failed and their corresponding lessons learned to apply to the BPS recovery effort:

|  | Major Causes of Failure | Major Lessons Learned |
| --- | --- | --- |
| 1. | ETF sponsorship did not act on project issues | Assign a single, experienced sponsor with sufficient availability |
| 2. | Ineffective overall project approach | Implement BPS in a phased approach versus a ‘big bang’ approach to manage scale and complexity risks |
| 3. | Inadequate ETF vendor management | Manage vendors versus trusting vendors. Require vendors to provide proof of their findings. Require vendors to provide sufficient explanations to ETF sponsors regarding project approaches and issue resolutions. Hold vendors to contract terms. |
| 4. | Lack of sufficient knowledge of key methodologies used within the team (all parties) | Ensure project team has experienced RUP and OO methodology leads (or other methodologies as needed). |
| 5. | No definition of completion with use cases or design activity | Ensure project team has experience in the skills needed to facilitate project tasks. See #4 above. |
| 6. | Over-engineered technical architecture | Ensure project team has experience with the technical skills needed. See #4 above. |
| 7. | Inadequate risk management and issue resolution processes | Use experienced project management resources |

- Monitoring Role

Based upon our brief assessment, following are the major reasons why the BPS Monitoring Role failed and their corresponding lessons learned to apply to the BPS recovery effort:

|  | Major Causes of Failure | Major Lessons Learned |
| --- | --- | --- |
| 1. | Fundamental and complete monitoring vendor failure to perform their intended role | Select a monitoring vendor that requires a hands-on approach to reviewing project plans, deliverables, issue logs, risk management plans and project management processes for progress. Confirm their expertise in managing large projects of the specific type being performed such as: custom projects using RUP and OO design approaches |
| 2. | Structure of the monitoring vendor role | Require that the monitoring vendor perform in a hands-on role and provide quantitative assessments of items such as earned value, checklist driven assessments of processes and deliverables etc. |
| 3. | Inadequate ETF vendor management | Manage vendors versus trusting vendors. Require vendors to provide proof of their findings. Require vendors to provide sufficient explanations to ETF sponsors regarding project approaches and issue resolutions. Hold vendors to contract terms. |

- DEG

Based on our brief assessment, the Department of Electronic Government (DEG) was not a root cause of the failure of the BPS project.  Our view is that the security dependency that the BPS project had on DEG should have been treated much like any normal project issue.  While it is true that ETF worked four months with DEG to negotiate project agreements, that negatively impacted the project timeline, it is understood by all that DEG was not a material cause of the overall failure of the project.  The BPS technical architecture itself, independent of any DEG security issues, was never proven.

- BPS Business Case

Based on our brief assessment, ETF’s benefit estimates appear to be both reasonable and conservative.  We have used these same benefit categories and estimates going forward.

Our five year total cost of ownership estimates range from $11.5 million to $19.3 million depending on whether a package or custom solution is selected as well as how various other estimating variables is considered.  Our estimating model will be revised by ETF over the next 3-4 months as next step activities are completed and more detailed information becomes available.

Go Forward Recovery Approach

Scope/Phasing

Together with members of ETF’s business and technology teams, we prioritized the various BPS scope components based on level of effort and impact on improving ETF’s environment to restructure the full BPS scope into seven separate phases to:

- Significantly reduce the risk of the project

- Create an initial scope that could be implemented within ETF’s remaining BPS project budget

- Allow ETF to build skills that could be used to implement later phases using a higher percentage of internal resources

The seven phases are:

- Phase 1:	Replace Annuity Payment System

- Phase 2:	Provide Internet Access and IVR/Call Center Integration to Annuitants

- Phase 3:	Replace Lump Sum Database

- Phase 4:	Interface with WISMART

- Phase 5:	Interface with HICS and Replace Accumulated Sick Leave Conversion

System

- Phase 6:	Integrate Workflow and Imaging with BPS

- Phase 7:	Integrate with Duty Disability Database or replace

* Open issues around security, cost, and long-term support exist around Internet access and workflow.  Additional analysis required in planning next steps.

We recommend an on-going process to reassess phasing decisions and establish scoping throughout the project lifecycle.  Business need should be the primary driver for phasing decisions.

Package versus Custom Solution

Based on our brief analysis of the RFI, the vendor provided adequate responses to the business and technical requirements where we determined that current package software solutions could be a viable alternative to custom development.  Approximately five years have passed since ETF initially embarked on the BPS project.  Since then, several potentially viable vendors have emerged.

Based on our research during this project there are up to four package software vendors that appear capable of fitting ETF’s short term and long term functional and technical needs.  Our research included:

- Issuing an RFI

- Conducting two 3 hour vendor demonstrations on core Phase 1 functionality

- Briefly following-up further on Phases 2-7 functionality fit

- Conducting vendor reference checks and

- Securing preliminary vendor pricing information

Assuming an appropriate level of fit to functional and technical requirements and reasonable purchase and maintenance pricing, we would recommend that ETF choose a package solution over a custom solution for the following reasons:

- Based on the fact that the benefit payment systems we reviewed have been implemented multiple times and a majority of the business functionality required is already defined and built, we feel the risk of Phase 1 and the overall risk of the implementation effort should be lower with a package.

- ETF’s on-going internal effort to maintain the package should be equal to or less than current state, requiring fewer internal resources at a time when managing headcount down and retaining key skills are an issue.  The cost of maintaining the package alternative may not vary significantly from the cost to maintain a custom solution based on the assumptions we have made in the cost model (see Appendix D)

- Some legislative changes may be easier to make in a package than in a custom solution or that the package vendor could be contracted to make the change possibly at a lower total cost versus a custom solution.  ETF should focus heavily on this issue when evaluating both package and custom vendors as this is a critical to the total cost of ownership.

Included within our immediate next steps recommendation, is a complete software selection process that is required to confirm the fit and viability of the package software vendors.  While these vendors are mature enough for ETF to thoroughly consider a package alternative, our view is that this set of vendors is still maturing and requires a thorough software selection process to mitigate any risks of selecting a seemingly strong vendor that turns out to be too immature to meet ETF’s needs.  Additionally, ETF will need to evaluate the total scope offered by these package software vendors to effectively assess the long-term total cost of ownership and benefit offered by these vendors.  However, we recommend that ETF only award implementation work initially for the Phase 1 scope.

It is our recommendation, that ETF conduct its software selection project as a ‘solution selection’ project where ETF considers both custom and package solution alternatives.  By following this approach, ETF can manage the timeline risks that would be associated with following a sequential package and then custom evaluation, complete more thorough analysis around both alternatives and create the best negotiating position for ETF as ETF selects its final approach and vendor.

Cost/Benefit/Timeline Summary

Following is the summary cost, benefit and timeline information for Phase 1 and the remaining six phases:

| Category | Custom | Package | Timeline | Notes |
| --- | --- | --- | --- | --- |
| Phase 1 external implementation costs | $3.8 - $5.1 million | $3.7 – $5 million | Package: 12-15 months Custom: 16-20 months | Package does not include estimated annual software maintenance of $250,000. |
| Total cost of ownership (internal and external) | $15.6 – $20.7 million | $14.5 - $19.3 million | Package: 4-5 years Custom: 5-7 years | Package includes total annual software maintenance of $1.05 million (approx $250,000 per year) |
| 5 yr. total benefit | $5.5 - $7.5 million | $8.5 - $11 million | N/A |  |

The cost estimate ranges shown above were developed using a -10% and +20% range around the actual estimate that was created for each phase.  Our actual estimates are supported by various cost models and matrices that are part of our final deliverable.  Within each phase, we also included a 30% estimating contingency factor to plan for unknown scope items, unknown complexities of known scope items and for managing and executing performance variances that may occur based on the actual skills assigned to the project both internally and externally.  We also used a planning assumption regarding what percent of total effort by phase would be completed using internal ETF resources versus external vendor resources.  We set the external vendor percent at the level that we jointly felt was needed to provide the required level of proven skills to each phase.  The remaining effort should ideally be done by ETF personnel to maximize ownership and knowledge transfer to allow ETF to support the new solution and most effectively manage its total cost of this project.  The aforementioned project roles are identified within the Project Roles tab of the Cost Model.

For Phase 1 estimating purposes, we have assumed that ETF will manage its internal resource capacity and project budget together to provide the required number of internal functional and technical resources to complete Phase 1 within the suggested time ranges to maintain project momentum.  Following are the required internal functional and technical resource requirements for the custom and package alternatives and using the timeline ranges shown above.

|  | Phase I Internal ETF Resource Request |
| --- | --- |
|  | Functional | Technical |
| Custom Implementation (16-20 months) | 4.0 resources: Jim Lodholz (75%) Lisa Allen (75%) Brian Schroeder (75%) Nadine Lacy (75%) Connie Koberle (75%) | 4.0 resources: Barb Rothwell (75%) Dave Cherry (75%) Jon Forde (75%) TBD (100%) |
| Package Implementation (12-15 months) | 4.0 resources: Jim Lodholz (75%) Lisa Allen (75%) Brian Schroeder (75%) Nadine Lacy (75%) Connie Koberle (75%) | 4.0 resources: Barb Rothwell (75%) Dave Cherry (75%) Jon Forde (75%) TBD (100%) |

Note: To calculate this average number of ETF FTE’s required for Phase 1 we used 80% of 2080 annual hours divided by 12 months to determine a monthly FTE productive availability of 139 hours.  We then took the number of estimated internal functional and technical hours from our estimating model divided by the high and low timeline range, divided by 139 hours to arrive at average ETF FTE required over each duration.  We further completed a capacity versus named resource availability by major segment of the project to confirm that our timeline is realistic.

Based on our current discussions with the ETF project teammembers, we understand that ETF anticipates it will be able to provide the required functional FTE to support this project.  ETF may want to develop a backfill and/or outsourcing contingency strategy to ensure it can meet any functional FTE shortfall.  The costs of the backfill/outsourcing contingency strategy need to be included in the cost models.  Currently there is a line item in the cost model but no dollars have been estimated.

For the technical FTE requirements, based on our discussion with ETF project teammembers, we believe that either ETF will be able to provide the required FTE or that since the internal cost of $76/hour is close to the expected external cost to acquire development resources that no budget item is needed.  Any changes in this assumption would require a corresponding update to the cost models.

For Phases 2-7, we are assuming that ETF will complete projects at a pace that is constrained by internal resource availability and that no budget line item is needed for backfill/outsourcing of internal ETF resources.  ETF could choose to accelerate or slow this timeline as it sees fit and make the corresponding adjustments to the cost models.

Based on our discussion with ETF management, ETF generally appears to have the appropriate skills and resources at the functional and technical team level to successfully implement Phase 1 with external support, and subsequent phases with a higher percentage of internal staff.  However, it is not clear whether ETF has the appropriate project management skills or available resources to properly manage the Phase 1 project.  ETF should evaluate their internal project management candidates and determine if any backfill or support requirements are needed.

Our Phase 1 estimate is based on a reasonably detailed activity driven estimating model (which is included in our final deliverable) and includes the following metrics:

| Cost Model Metrics | Phase 1 |
| --- | --- |
| Number of Use Cases | 127 |
| Number of Iterations | 5 |
| Number of External Systems to Modify | 3 |
| Number of Conversions | 3 |
| Number of Interfaces | 22 |
| Number of Reports | 60 |
| Ave % Pre-Defined (Package) | 50% |
| Number of End Users (Main) | 40 |
| Number of End Users (Read-Only) | 110 |
| Total Cost Metrics |  |
| ETF Blended Staff Rate (incl 36% benefits) | $ 76 |
| External Project Mgr Rate | $ 175 |
| External Funct/Tech Staff Rate | $ 150 |
| Training Days (by phase) | 20 |
| External Training Cost per Day | $ 2,000 |
| Monitoring Cost per Hour |  |
| Project Monitor Business Analyst | $ 200 $ 150 |
| Other: |
| 30% total contingency over the bottom-up estimates |
| -10/+20% total cost range |

The following major cost drivers need to be refined during the recommended next step activities:

- Resource backfill contingencies to offset any internal resource shortfalls

- Legislative change project costs are not included in our cost estimating model as these are not viewed to be project costs.  However, the cost savings difference between package and custom solutions is included within our benefits estimate

- Re-engineering of any business processes to establish process improvement opportunities

- On-going personnel support and maintenance costs are not included since they are viewed to be equal to or less than the current support costs

Need for Monitoring Vendor Role

While the scope and cost of the new Phase 1 project is significantly less than the prior full BPS project, Phase 1 still represents a significant project investment for ETF given the Department’s lack of prior experience implementing large scale projects using methodologies (i.e. Rational Unified Process, Object Oriented framework) new to ETF.  Also considering ETF’s need to deliver the recovered project successfully, following the termination of the previous BPS project, we believe this additional risk management measure is warranted.

For this reason, we recommend that a hands-on monitoring vendor role be used for Phase 1 to provide ETF with sufficient project management oversight and project sponsor support/coaching for this project.  A critical success objective for this Phase 1 monitoring vendor role will be to provide ETF’s executive, business and technology leadership with the necessary tools to allow ETF to complete future phases without the assistance of a monitoring vendor.

We would like to further stress that, in our view, the failure of the prior monitoring vendor/role was driven by the way the role was structured as a hands-off monitor combined with the fundamental and complete failure of the monitoring vendor to perform in its intended role.  ETF should in no way misconstrue this unfortunate experience with the value that can be gained from a suitable monitoring vendor that is acting in a hands-on capacity to offset internal experience shortfalls.

Immediate Next Steps

Create RFP Project Charter

ETF should first complete a formal project charter for the RFP project to set the scope and develop the project plan for this activity.  Within this activity, ETF should pay particular attention to defining the scope boundaries it wishes to use when evaluating the package software alternative.  As noted above, ETF should consider a broader scope consisting of Phase 1-7 scope at a minimum when evaluating the package alternative. ETF should also remain open to new ideas that may be presented by package vendors such as solutions they offer to replace related ETF scopes such as the single demographic database for example.  At the same time, ETF needs to control the scope of the package evaluation and focus substantial effort on confirming Phase 1 fit.  Tightly coupling an RFI to define the Phase 2-7 requirements with a Phase I RFP, in addition to conducting scripted vendor demonstrations, will allow ETF to award a Phase I contract while gaining a broad understanding of vendor fit and viability for future phases.

ETF should also include the selection of a project monitor within this charter.  The actual project monitor selection process cannot begin until a final package or custom solution is chosen so that the specific skills required by the project can be acquired.

Complete Solution Selection Project

ETF should complete a formal, thorough solution selection process including taking

- Package vendors through detailed demonstration scripts, fit gap analysis, reference checks and final total cost of ownership analysis

- Custom vendors through a series of demonstrations (technical capabilities, prototypes, methodology), reference checks and final total cost of ownership analysis

- Monitoring vendors through detailed demonstrations of methodologies and tools to support their QA/QC activities and reference checks

- The selected vendors through detailed contract negotiations where specific critical skills are secured and any appropriate performance requirements are defined.

Skills and Impact Assessment

Once ETF has finalized its solution selection, ETF should also conduct a skills and impact assessment to determine what skills and support structures will be needed to support any new technologies and processes.

Based on our discussions with ETF, we understand that ETF is planning to complete these immediate next step activities using internal resources.  Therefore, we have not estimated any external costs to support these activities.

# Section II: Project Post Mortem Analysis

## A. 	BPS Project

Based upon our brief assessment, following are the major reasons why the BPS project failed and their corresponding lessons learned to apply to the BPS recovery effort:

| Major Causes of Failure | Major Lessons Learned |
| --- | --- |
| 1. ETF sponsorship did not act on project issues 2 separate sponsors, one each for technical and functional areas did not allow for effective issue resolution and created communication challenges with the vendors Lack of sponsor(‘s) experience in directing large scaled projects with a level of complexity Less than required sponsor availability to participate in the project resulting in a reactive sponsorship posture as needs arose versus a proactive posture to ensure success Sponsor changes during the project Authority not given to steering committee to act on issues and concerns Vendors were in a position to make decisions | 1. Assign a single, experienced sponsor with enough time Overall responsibility and authority needed by sponsor for driving both functional and technical decisions. This will be especially important for ETF since historical challenges appear to exist between IS and the business that will require effective issue resolution at a project level. Single point of contact for issue escalation/resolution Experience that allows the sponsor to assess true project progress Able to invest adequate time on the project to proactively ensure success |
| 2. Ineffective overall project approach As the project functional and technical scope grew significantly from its inception in 1997, the project approach did not change accordingly to effectively manage the significantly increased risk and complexity Big bang approach was used, for a large scope/high risk project, without commensurate risk management/skills in project management and functional/technical team leader roles | 2. Implement BPS in a phased approach versus a ‘big bang’ approach to manage scale and complexity risks Prioritize key functions into manageable efforts to implement Ensure that the level of project management and key skills are adequate to match the level of risk/challenge presented by the project. Develop approaches to over-manage key risks as appropriate |
| 3. Inadequate ETF vendor management It is not clear whether ETF had the experience or right process/rigor in place to conduct a thorough/effective vendor selection process. We did not investigate this idea in any detail and rather suggest it may be a lesson learned/area of focus going forward. ETF ‘trusted’ the vendors to do their jobs versus managing the vendors and taking ownership over project approach and decisions In ETF’s defense, a monitoring vendor was chosen. However, that monitoring vendor failed in its capacity. Furthermore, ETF was not able to take action to fix or replace the failing monitoring vendor | 3. Manage vendors versus trusting vendors Select proven vendors using experienced vendor selection personnel and processes Define required vendor skills and ensure they are provided by the vendor Require right project management deliverables be produced such as work plans Ensure ETF understanding and ownership over vendor approach and key deliverables/decisions Enforce contract terms as appropriate Ensure ETF sponsor and steering committee have access to terms and condition of the contract. |
| 4. Lack of knowledge of key methodologies used within the team (all parties) The team did not know how to use Rational Unified Process (RUP). Without RUP experience, the team misused RUP approaches such as iterations and got lost in the many details of producing RUP documents that provided little or no value The vendor team did not have experienced Object Oriented (OO) designers resulting in an over-engineered technical architecture | 4. Ensure project team has experienced RUP and OO methodology leads (or other methodologies as needed). Ensure vendors are not learning on ETF’s project |
| 5. No definition of completion with use cases or design activity Use case guidelines and standards were lacking Inadequate quality assurance to support use case process Related to the lack of RUP experience, team members did not know when a use case was completed, contributing to significant ‘spinning of wheels’ likely accounting for many unproductive months of the project timeline | 5. Ensure project team has experience in the skills needed to facilitate project tasks. See #4 above. For critical deliverables such as use cases, establish standards that define level of detail and completeness requirements Quality assurance process to provide accurate and consistency |
| 6. Over-engineered technical architecture While this occurred due to #4 above, it resulted in a technical architecture that could not be used to prove a single use case Architecture was developed concurrent with use case and requirements gathering, which did not allow for interaction and guidance The tangible failure of the technical architecture ultimately led to the decision to stop the project | 6. Ensure project team has experience with the technical skills needed. See #4 above. Let real business requirements from the use cases drive the level of technical architecture complexity. |
| 7. Inadequate risk management and issue resolution processes While ‘administrative evidence’ of these processes exists (i.e.: filled out templates), ‘real’ risk management and issue management does not appear to have occurred. This is likely due to a lack of experienced project management and team leadership throughout the project | 7. Use experienced project management resources Gain real value from these processes versus complying with them administratively. Action items and responsible parties should be assigned and be accountable for resolution |

See Appendix A for details regarding BPS Post-Mortem

## B. BPS Monitor

Based upon our brief assessment, following are the major reasons why the BPS Monitoring Role failed and their corresponding lessons learned to apply to the BPS recovery effort:

| Major Causes of Failure | Major Lessons Learned |
| --- | --- |
| 1. Fundamental and complete vendor failure to perform their intended role While the use of a monitoring vendor is a best practice and can work very successfully, for whatever reason, MAXIMUS, Inc. did not supply the level of talent, effort and/or approach that was required to fulfill their monitoring role MAXIMUS, Inc. specifically did not provide the talent required to conduct any level of QA over a RUP/OO type project. nVISIA was a subcontractor and appeared to have the right technical skills-however, on a limited frequency and much too late. The status reports provided by MAXIMUS, Inc. are virtually void of any value that would help a project sponsor identify and manage project risk or to understand project progress The level of failure was so fundamental and so complete that we did not conduct much additional analysis of this role. | 1. ETF must define what skills, approach and level of effort are required of a monitoring vendor, select a qualified vendor and manage the vendor Ensure the procurement process works to secure the right skills and the right level of experience Validate the responsibilities of a vendor and whether or not it is needed |
| 2. Inadequate ETF vendor management ETF sponsors were unable to detect and/or did not act on the vendor’s failure to deliver in their role ETF did not enforce contract terms that required that certain deliverables be completed | 2. Select a qualified vendor. Ensure ETF understanding and ownership over vendor approach and key deliverables/decisions Enforce contract terms as appropriate |
| 3. Structure of the monitoring vendor role The monitoring vendor role was structured such that a once per month visit was conducted involving a brief review of selected documents, participation in a steering committee and production of a summary monitoring report each month. Effective project monitoring for a project like this requires significant hands-on approach and deliverable review and more detailed follow-up on key issues on an as needed basis. | 3. Manage the vendor relationship. Monitor on-site regularly |

See Appendix A for details regarding Monitor Post-Mortem

## C. Department of Electronic Government

Based on our brief assessment, the Department of Electronic Government (DEG) was not a root cause of the failure of the BPS project.  Our view is that the security dependency that the BPS project had on DEG should have been treated much like any normal project issue.  While it is true that ETF worked four months with DEG to negotiate project agreements, that negatively impacted the project timeline, it is understood by all that DEG was not a material cause of the overall failure of the project.  The BPS technical architecture itself, independent of any DEG security issues, was never proven.

## D. BPS Business Case

Based on our brief assessment, ETF’s benefit estimates appear to be both reasonable and conservative.  We have used these same benefit categories and estimates going forward.

Our five year total cost of ownership estimates range from $11.5 million to $19.3 million depending on whether a package or custom solution is selected as well as how various other estimating variables is considered.  Our estimating model will be revised by ETF over the next 3-4 months as next step activities are completed and more detailed information becomes available.

We did not do a detailed reconciliation of our estimating approach with the original BPS cost estimating approach as part of this project.

## E. Development Approach, Use Cases and Technology Architecture

As part of our evaluation, we focused particular attention on evaluating the technology architecture and use case results and directions of the failed project as these were seen to be:

- Potential significant causes of the BPS failure

- Areas of hoped for significant reuse going forward

- Areas of concern regarding fundamental design and long term viability

We have organized our assessment findings for this area into three topics:

| Topic | Summary Finding |
| --- | --- |
| RUP Development Process | Team lacked sufficient RUP skills No iterations-big bang approach A likely cause of wasted effort filling out mandatory RUP templates without knowledge of why and without progressing the design |
| Use Case Requirements Process | Team lacked sufficient use case skills A significant potential cause of ‘churning’ 80%+ reusability is based on the intellectual property already captured in previous efforts. Need to revisit each use case and align with new implementation strategy; some re-factoring activities remain to establish use case completion and consistency. |
| Technical Architecture Design | Over-engineered, too complex Did not leverage available patterns sufficiently Was not understood by ETF team 5-10% reusability is based on the fact that the architecture framework was deemed unusable in its current state; however, the supporting utility modules could be extracted and considered valuable in the go-forward custom approach. |

### RUP Development Process

Current custom software development best practices suggest that an iterative, incremental process is best to manage the risks of technical architecture and evolving business requirements.  The BPS system was to follow the Rational Unified Process (RUP); however, it is evident from the existing artifacts that the RUP was used mostly as an artifact delivery method (documentation) rather than as an iterative and incremental process.  RUP is a very large and robust methodology that is usually applied in selective fashion.

The project team did not appear to have sufficient RUP experience and therefore did not practice selective use of the RUP methodology.  There was no evidence that an iterative or incremental process was in-place.  Based on our review of many of the RUP deliverables, the project team appeared to be ‘filling out’ required RUP documents versus truly using RUP to manage the development process.

Though proper use of the methodology alone likely would not have prevented the project from failure, it would have exposed some of the use case and architectural limitations early in the process and provided the management team with an improved ability to react.

### Use Case Requirements Process

A modern custom design technique called ‘use cases’ was used to define the BPS requirements.  We used use case best practices to assess the use cases that were created on the BPS project and developed the following findings:

- Some of the existing use cases describe features rather then the systems behavior in response to an action. Use cases should be scenarios and not functional requirements; there are other artifacts that are better suited to capture functional requirements.

- Some of the use cases are being used as class and/or data specification. This kind of information should be captured in a conceptual model (class and data model). Use cases should only document behavioral requirements.

- Some use cases have references to user interface (UI) elements. This information is not required by a use case nor should it be there.

- The use cases are not consistent. It is arguable as to what should and should not be in a use case; however, consistency in creating use cases against an agreed upon template standard will allow for better communication.

- Some use cases have repetitive or common behaviors. These repetitive and common behavioral functions should be documented as separate use cases, and included into others (stereotype <<include>>, <<extend>>, <<uses>> etc).

- Some use cases seem to have been reverse engineered from existing system(s) or functionality, and are being driven by a UI design.  Allow for the use cases to drive the new functionality and presentation, not the other way around

- There are no activity diagrams that support or complement any of the use cases.

Based on our review, similar to the usage of RUP, the project team did not appear to have sufficient use case development experience and did not follow use case design best practices.  Instead, they defined how the system should function rather then what functionality the system should provide.  Further, some of the use cases contain great deal of business and data rules that should not have been included in use cases, making them much more complex and less comprehendible.

The impact on the project of not following use case best practices and not having a standard template that defined when a use case was done appears to be that the team may have ‘spun its wheels’ in too many use case design and review sessions, never knowing when they were done.  This may explain how the portions of the team could have been ‘busy’ for 20 months without producing much finished product.

At the same time, almost all use cases provide a good starting point for the recovery project and are highly reusable with some rework and modification to match the new scope phases and to ‘true them up’ against a defined use case template and completion standard.

### Technical Architecture Design

Note:  Given the significant complexity of Object Oriented design principles, we have only summarized our technical findings below.  For those readers of this document that require a more technically complete understanding of our findings, they should discuss our findings in person with the ETF technical team members that participated in our BPS project evaluation project.

In evaluating the existing BPS architecture from a purely Object Oriented, theoretical point of view, the system architecture uses proven OO concepts and design patterns.  However, just because the design follows good OO principles does not mean that the system is easy to implement or maintain.

The unnecessary use of specific OO patterns in the current BPS technical architecture added a great deal of unnecessary complexity to the system, making it difficult for developers to understand it.

The architectural design of the BPS system is limited to the ‘framework’.  The main focus of the framework was on the underlying “plumbing” of the system and not on addressing the problem domain.  The architectural approach is extremely complex.

As a result, in evaluating the existing source code, it was determined that it was incomplete and that its reusability level is estimated to be very low (No more than 5% – 10%).

The following simplified diagram attempts to explain how the BPS project had approached the technical design and what problems exist with the current design.

At this high level, there is little to disagree with in the overall vision of the BPS architecture.  Indeed, the diagram above represents a fairly typical layering for web-based systems.  In our view, the major technical problems with the BPS architecture resulted from the implementation of this basic model, rather than any unworkable characteristics of the high-level model itself.

In reviewing architecture design documents, and interviewing several members of the technical team, we have made the following observations:

- The architecture was over-abstracted and over-engineered, and was designed to anticipate all possible future contingencies, instead of focusing on known requirements.  Specifically:

  - The web tier used an overly complex mechanism for managing end-user session state.  The web tier also did not leverage standard libraries for Java-based web development, instead relying on a custom framework.

  - The design of the rules engine was at once too ambitious, and yet not powerful enough to handle typical application rule scenarios.

  - The domain model consisted of business objects that were simple data structures, with no encapsulation.  Instead, all business logic (even simple validations) was externalized into a separate layer, increasing the overall complexity of the system.

- The architecture had as an explicit goal using every available feature of the J2EE specification (including EJB entity beans), instead of using only those features that added demonstrable value to the solution.

- The architecture and use case development occurred concurrently which did not allow for interaction and timely inputs to the design process.  When it came time to test the architecture it was identified that the architecture did not support the functionality and requirements.  The frame work was deemed too complex.  Feedback between the functional team and development team throughout the design phase could have been used to refactor the design in more appropriate directions along the way.

- The excessive layering of the architecture presented a barrier to developers trying to learn the architecture and use it to build applications.  Most significantly, several features of the framework ran counter to accepted J2EE programming idioms, and relied on a series of “implicit” rules to work correctly.

- The complexity of the architecture made debugging of the system extremely difficult and time consuming.

- The framework did not appear to be designed to facilitate unit testing or performance measurement.

In short, the BPS technical architecture suffered from being designed to be “all things to all people,” rather than being designed to address specific problems and being refined as additional requirements were identified.  Because of the sequential process used to design and implement the architecture, many of these problems were not apparent until it was too late to correct them.  In our view, very little of the BPS architecture can (or should) be carried forward to the development of a new system.

# Section III: Go Forward Recommendations

## A. Revised Implementation Strategy

The original BPS project scope is considered too big to implement at once.  In going forward with the BPS recovery projects, it is suggested that ETF implement projects in smaller sized efforts to more effectively manage risks, build skills and accelerate benefits.

To facilitate establishing the priorities of the business functions, we created an overall system diagram to show how all of the entities involved in the Benefit Payment Systems worked together.  Together with the functional and technical teams we were able to create the following diagram which represents the main interface and integration point dependencies:

Next, together with ETF personnel we were able to prioritize the many individual BPS components according to impact on ETF’s environment and effort.  Based on this priority ranking, we then created seven separate implementation phases.  ETF could combine some of the items listed in Phase 2-7 if needed to meet new needs and priorities.

The following scale defines how the Impact and Effort scoring was established:

| Impact (1 = Low Impact, 10 = High Impact) | Effort (1 = Low Effort, 10 = High Effort) |
| --- | --- |
| Number of people or departments impacted | External constraints to consider (legislative, DOA) |
| Potential improvement from current | Complexity |
| Risk of not doing it | Resources required |
|  | Cost |

The rationale behind grouping Phases 1-7 was to have the business team identify logical units of work while understanding Phase I was to provide basic functionality only (i.e. no frills).

After Phase 1, there are few dependencies that exist among the remaining phases.  It is recommended that ETF conduct scoping exercises before starting each initiative to appropriately prioritize the business needs at that point and time.  In addition, the business case for Phase 2, self service Internet, remains unproven.  As a result, the order in which Phases 2-7 are implemented is subject to change.

Please see Appendix B for the rationale, phase definition, dependencies, and risks associated with each phase.

## B.  Package Alternatives and Solution Overview

Based on our brief analysis, we determined that current package software solutions are a viable alternative to custom development.  Approximately five years have passed since ETF initially embarked on the BPS project.  Since then, several potentially viable vendors have emerged.

Based on our research during this project, there are up to four package software vendors that appear capable of fitting ETF’s short term and long term functional and technical needs.  Our research included:

- Issuing an RFI

- Conducting two 3 hour vendor demonstrations on core functionality

- Briefly following-up further on phase 2-7 functionality fit

- Conducting vendor reference checks

- Securing preliminary vendor pricing information

Included within our immediate next steps recommendation, is a complete software selection process that is required to confirm the fit and viability of the package software vendors.  While these vendors are mature enough for ETF to thoroughly consider a package alternative, our view is that this set of vendors is still maturing and requires a thorough software selection process to mitigate any risks of selecting a seemingly strong vendor that turns out to be too immature to meet ETF’s needs.  Additionally, ETF will need to evaluate the total scope offered by these package software vendors to effectively assess the long-term total cost of ownership and benefit offered by these vendors.  However, we recommend that ETF only award implementation work initially for the Phase 1 scope.

It is our recommendation, that ETF conduct its software selection project as a ‘solution selection’ project where ETF considers both custom and package solution alternatives.  By following this approach, ETF can manage the timeline risks that would be associated with following a sequential package and then custom evaluation, complete more thorough analysis around both alternatives and create the best negotiating position for ETF as ETF selects its final approach and vendor.

The following table shows the retirement systems we contacted to discuss their experience regarding custom or package solutions.  In general, the package route provided more functionality in less time, at less cost than the custom route.  There also appears to be a higher degree of project failure with the custom route, as packages are often selected after a custom route has failed, even failing more than once.  The timelines and costs are dependent on each systems situation.  The contact names and numbers are listed for ETF to follow-up for their own due diligence.

We used a structured approach to review the feasibility of package software solutions to meet ETF’s requirements.  After defining ETF’s critical phase 1 requirements, a Request for Information was sent to 6 vendors to gain feedback on functional fit.  Two vendors, Vitech and CPAS/Tier provided a 3-hour demonstration and question and answer session regarding their product to ETF functional and technical staff to confirm initial feasibility.  Based on those demos, it appears the package software solution could meet a high degree of critical requirements.  Below is a summary of the scoring based on vendor responses to the RFI.

Please see Appendix C for further details regarding the vendor identification and process.  Also available are the RFI responses from all participating vendors.

Total Cost of Ownership:  Package

We developed a total cost of ownership based on the phased scope approach identified above.  We used several sources of information, including quotes from vendors and detailed implementation cost model for package.  Key findings on our TCO assessment:

- With a package solution, Phase 1 is estimated between 12-15 months with total estimated external costs between $3.7 and $5 million.

  - Internal staffing costs are estimated between $1.6 and $2.1 million.

  - Vitech provided an estimate for phase 1 of approximately $3 million.

  - Ohio Police and Fire is currently implementing Vitech, end-to-end in 2.5 years at a total cost of $7.2 million.

- All phases are estimated to be complete in 4 to 5 years at a total estimated external implementation costs between $7.8 and $10.4 million.  In addition, software maintenance costs are estimated at $250,000 annually.

- Total cost of ownership over 5 years, including annual software maintenance and internal project staffing costs, are estimated between $14.5 and $19.3 million.

- Costs by phase and costs by year will be different, as the timing of phases may be spread across multiple years and the year breakdown includes the annual software maintenance fees.

- With a package solution, the phases that can be completed by year are shown below.

- The associated costs are based on quotes obtained from Vitech. Further, it also supports the statement from Vitech that they are compatible with DB2.

Please see Appendix D for detailed cost model and assumptions

Return on Investment: Package

There is a significant cost savings by replacing the current annuity system.  ETF must replace their current annuity system.  The current annuity flat file system, built in 1977, has inherent system limitations (i.e. system cannot handle retroactive withholding amounts; regular withholding up to $9,999, and retro limited to $999), is inflexible and costly to address legislative changes, and a growing retirement population continues to put a significant resource strain on ETF.  The current system does not allow users the ability to update the critical data online, using a 3rd party to key in changes based on manual forms ETF sends out regularly.  Overall, the current system is expensive to maintain and complex to change.

Key findings on our cost savings assessment:

- With a package solution, the total 5 year benefit is estimated at $8.5 and $11 million.

- The majority of hard-dollar cost savings comes from the ability to adapt to legislative changes with 25% less cost than currently.  Legislative changes are estimated at $5.7 million per occurrence (based on Act 11) in the current system.  Estimated to occur twice in 5 years.  Cost savings of 75% expected as majority of legislative changes can be addressed with existing package setup by modifying effective date business rule settings.

- Many intangible benefits exist and they are listed below.

Note:  Year 2005 does not show benefit because this would be the implementation period.  It is also noteworthy that the call center cost avoidance of 1 FTE/yr. may be too aggressive.  We were not able to confirm this assumption.

Intangible Benefits of Package vs. Custom or current Legacy

- Potential to transform ETF vision to move all systems to single, integrated solution that includes BPS, WEBS, and HICS functionality.

- Inherently provides business process efficiencies, as tools such as queries, audit trails, and workflow are built within the packages.

- Business rules maintained by business units can change system for legislative changes by modifying rules stored within tables versus current annuity file structure.

- Data is maintained in a real-time, shared database, thereby eliminating paper shuffling and multiple points of data entry.

- Vendor support includes updates to tax tables or legislative changes that impact the system.

- Eliminates manual work-arounds to handle current annuity system limitations such as handling retroactive withholding greater than $1,000 or handling benefits over $1,000,000

- Provides potential for annuitant self-service to look up or change data on their own through a secured website.  This will reduce call center volume and other program costs significantly.

Approach: Software

If a package software solution is selected, we estimate Phase 1 can be completed in 12-15 months, using the following iterative approach.  Future phases would follow the same general approach.  This approach may be changed slightly based on the chosen vendor, but it should still cover the major components outlined below.

A key premise of the package approach revolves around the business modeling activities.  We recommend the business modeling and system configuration occur in several iterations within each phase.  One activity prior to business modeling is to review all requirements that are part of the phase, and define an iteration plan.  For example, in phase 1, iteration 1 should begin with the basic core requirements of the system (i.e. produce one check for one account), and iteration 2 would build on iteration 1 (i.e. consolidate multiple accounts for one check).  The project task of refining the implementation estimated 5 iterations in phase 1.

The use cases, as they exist today, can be used as the driver to define system requirements and configuration settings.  We recommend using teams of 3-4 ETF/Vendor analysts that review the use cases and turn them into system configuration decisions.   Within each iteration, the system is configured and a unit test is performed.  Appendix D includes a cross reference of requirements to use cases to facilitate this process.

Alternate Vision:  Replace WEBS and HICS with Single Integrated Solution

Based on our brief assessment of potential package solutions, there may be a possibility to consider replacing WEBS and HICS with an integrated solution, in addition to replacing the current Annuity Payment System. Both packages we reviewed (Vitech and CPAS) provide end-to-end retirement system functionality, including active employee management (enrollment/contributions), health insurance management (eligibility/billing) and benefit payment.  Making this decision is dependent on several key assumptions:

- Comprehensive Total Cost of Ownership defined for entire solution.

- Long-term vision established to move to single, integrated solution

- Selection of vendor that provides end-to-end solution

- Short-term timeline and ability to consider larger scopes

- Prior investments already made by ETF that preclude these options

Assuming this is a feasible, long-term option, ETF should reconsider their phases.  A single package solution does not eliminate the need to move forward in a phased approach, however, the order of priority would potentially shift to the following:

- Replace current Annuity System (same as planned) with BPS solution

- Replace WEBS with BPS solution

- Replace HICS (including replacing ASLCC functionality) with BPS solution

- Provide Internet Access / IVR Integration

- Replace Lump Sum Payment Functionality

- Interface with WiSMART

- Integrate Workflow / Imaging

- Move Functions of ICI/LDTI In-house

Several potential advantages this approach may have:

- Single, integrated system eliminates many interfaces between disparate databases that are costly to maintain.

- The need for a custom developed Single Demographic Database is eliminated, as this function could be replaced by a single, integrated system.

- Programs like system-wide Reconciliation and LDTI functions are already part of the package and are a long-term vision.

- Single place to manage legislative or business rule changes.

- Simplify support and maintenance process, as the majority of support goes through single vendor.

- Based on the configuration of the solution, this may potentially limit dependence on DET and the annual processing costs for it.

- Transforms skills required by ETF staff to maintain system

The total cost of a package solution, including licensing and implementation, has not been defined.  This should be done as part of a total cost of ownership analysis.  The Ohio Police and Fire Pension Fund, who has 30,000 active lives and 20,000 retired lives, are implementing Phase 3 of 3 (expected in June 2005) for the full end-to-end Vitech solution in an estimated 2.5 years at a cost of $7.2 million.

The diagram below depicts a potential long-term vision for a single, packaged solution.  Notice that many of the integration points between BPS, WEBS, and HICS are eliminated because the potential package includes these modules that sit on the same database and share information across modules.

## D. Custom Build Overview

The custom build option remains a viable solution.  While package is preferred, assuming fit and cost, custom is equally viable.  With proper management and execution the option can be effective.

Total Cost of Ownership: Custom

We developed a total cost of ownership for custom based on the phased scope approach identified above.  Our detailed implementation cost model that was used to build our estimates is included in Appendix D.  Key findings on our TCO assessment include:

- With a custom solution, Phase 1 is estimated between 16-20 months with total estimated external costs between $3.8 and $5.1 million.

  - Internal staffing costs are estimated between $2 and $2.7 million.

- All phases are estimated to be complete in 5 to 7 years at a total estimated external implementation cost between $8.6 and $11.5 million.

- Total cost of ownership, including internal project staffing costs, are estimated between $15.6 and $20.7 million.  Note that workflow, imaging, and duty disability are estimated in year 6 and 7 this total cost estimate includes those costs.

- Costs by phase and costs by year will be different, as the timing of phases may be spread across multiple years.

- With a custom solution, the phases that can be completed by year are shown below.

Please see Appendix D for cost model details and assumptions

Return on Investment: Custom

Cost savings for the custom approach addresses the same critical needs as the package alternative.  The custom approach will develop a solution that is component based, allowing for less complex and costly changes for legislative changes.  The cost savings for custom versus package is 33% less, or $6.3 million for custom versus $9.4 million for package.

Key findings on our cost savings assessment:

- With a custom solution, the total 5-year cost savings is estimated at $5.5 and $7.5 million.

- The majority of hard-dollar cost savings comes from the ability to adapt to legislative changes at 50% less cost than currently.  Legislative changes are estimated at $5.7 million per occurrence (based on Act 11) in the current system.  Estimated to occur twice in 5 years.  Cost savings of 50% expected as majority of legislative changes can be addressed with existing package setup by modifying effective date business rule settings.

- Several intangible benefits.

Note:  Year 2005 and 2006 do not show benefits because this would be the implementation period.  It is also noteworthy that the call center cost avoidance of 1 FTE/yr. may be too aggressive.  We were not able to confirm this assumption.

Intangible Benefits of Custom vs. current Legacy

- Provides business process efficiencies such as online access to data and reports.

- Business rules maintained by business units, and can change system for legislative changes by modify rules stored within tables.

- Data is maintained in a real-time, shared database, thereby eliminating multiple points of data entry and potential data errors.

- Eliminates manual work-arounds to handle current annuity system limitations such as handling withholding greater than $1,000 or handling benefits over $1,000,000.

Approach: Custom

As discussed in the Post-Mortem, the failure of the original BPS project resulted as much from the development process used as it did from specific architecture and technology issues.  From a custom software development perspective, the major problems included:

- A linear, waterfall-like development process that made it difficult to validate the proposed architecture and to accurately measure actual progress

- Too much up-front focus on paper specifications and deliverables, and not enough on working software components

- A technical team structure that segregated developers working on the architecture from those expected to build applications using the architecture

If a custom development approach is selected for the going-forward BPS project, it is essential to define a workable development process that it tailored to the size and scope of the project, the technologies used, as well as the skills of the team members.

## E. Project Team Structure

Following is a suggested project team structure for ETF to use when restarting the BPS project.  We have included a brief description of the roles and responsibilities for each position in the project team structure.  We have also included specific organizational lessons learned from the post-mortem assessment in these comments where appropriate.

BPS Steering Committee

The Steering Committee should consist of senior leadership from the Secretary’s Office.

Rather than invoke a list of representatives from various areas of the organization to obtain consensus in the decision-making process, the goal of this role is to remain focused, in-control, and keep the project on-track in its effort to meet the project objectives.  The Steering Committee will be responsible for:

Communicating project vision and policy in their parts of the organization

Communicating and advocating any changes in their parts of the organization

Providing key input into decision-making and issue resolution processes from their unique vantage points

Ensuring resource commitments from their areas are met

BPS Project Sponsor

The Project Sponsor should be a member of the executive management team that sits above the IT and business areas that are included on the Steering Committee.  The Project Sponsor should be responsible for:

- Managing project scope

- Ultimate project success including on-scope, on-time and on-budget minimum metrics

- Using quantitative project management evidence regarding project status and issues to determine what corrective and/or preemptive actions need to be taken during the project.

- Leveraging the project monitor vendor to conduct detailed follow-up on any project progress or issue points that is required to ensure the project sponsor has complete and accurate understanding of the project status, risks and corrective action alternatives.

- Removing any roadblocks that impede the progress of the project

- Clearly communicating the “big picture” and any known impacts (positive or negative) to all levels of management

- Objectively resolving issues related to balancing competing business/functional and technical needs

- Ensure solution and monitoring vendor contracts are enforced

Project Monitor

The Project Monitor should report to the Project Sponsor, but should also work closely with the Project Director.  The contributions of the Project Monitor will ultimately depend on the management strength and skills of the Project Manager.  As a result, the responsibilities of the Project Monitor will throttle throughout the project; weighing in areas where the Project Management is lacking and backing off where the Project Manager is capable.  The Project Monitor’s participation with the following responsibilities includes, but will ultimately vary in:

Conducting proactive assessments of all project management and project delivery methodologies against best practices to identify any gaps and to recommend suggested actions to close any gaps

Review the project risk management plan to confirm that all key risks have been identified and that appropriate risk management action plans have been developed.  Conduct reviews of the risk management plan on a monthly basis and identify any new risks or new risk mitigation plans that are needed.

Conduct frequent reviews of all project status/progress reports to assess schedule and cost performance versus plan and to complete a revised schedule and cost forecast for all remaining work, focusing on critical path tasks.  It is assumed that the project monitor will be reviewing detailed workplans, task estimates and earned value reports to complete this assessment.  It is further assumed that the project monitor will review all critical deliverables and a sample of other deliverables to confirm the earned value reporting is reliable.  As part of this activity, it is assumed that the project monitor will work closely with the project manager to confirm any findings and to jointly determine corrective action alternatives and recommendations.

Conduct bi-weekly reviews of the project issues list to assess the number and severity of items on the issue list focusing on cross functional issues.  Conduct issue resolution documentation reviews to confirm that an effective issue resolution process is in place to ensure the right people are involved in resolving issues, effective alternatives and impact analysis is taking place  and that issue resolution impacts are rolled into the project plan to ensure all design decisions are implemented effectively.

Conduct quality reviews of all major deliverable milestones to ensure the quality of work product that has been completed.  Exit checklists/criteria for phases and individual deliverables should be used to support this analysis.  Selected interviews with ETF staff responsible for understanding the designs should also be completed to confirm that effective knowledge and ownership transfer is taking place.

Provide written project assessment reports to the project sponsor and project director on a bi-weekly or monthly basis as appropriate at each stage of the project.

Conduct one-on-one discussions with the project sponsor and project director to ensure they understand the project risks, implications and alternative actions that could be taken.

Complete any specific additional research requested by the project sponsor or project director to ensure they have full understanding of the project status and issues.

Project Director

- Manage project scope

- Ensure the needs of the business are identified and met/presented to the steering committee for approval

- Ensure the needs of IT are met/presented to the steering committee for approval

- Manage the project risk management plan.  Understand the issues.  Ensure actions are taken.  Understand the results of the actions and establish corrective action.

- Manage the project issue list.  Understand the issues.  Ensure actions are taken.  Understand the results of the actions and establish corrective action.

- Ensure project resource requirements are known and communicated to the responsible areas.  Raise critical resource issues to the project sponsor and steering committee with suggested corrective action plans.

- Ensure ETF knowledge transfer and ownership is taking place.

- Understand project progress and corrective actions required to address any cost and schedule variances.

- Ensure the proper ETF subject matter experts are actively involved in providing input to the project and reviewing key deliverables.  Ensure a meaningful signoff process is taking place.

- Meet regularly with the project monitor to compare understandings of the project status and resolve any gaps.

Project Manager

The Project Managers will provide overall project management, guidance and direction on a daily basis to the project team. The project manager role will include the ETF Project Manager and the BPS Vendor Project Manager. Project Managers will be responsible for overseeing the team leads, and will report directly to the Project Director. Responsibilities include:

Overall project planning, resource acquisition and work assignment responsibilities etc.

Establish project milestones, track project performance, and adjust project plans and staffing to ensure cost effectiveness and timely delivery

Leading risk management and issue management activities and suggesting corrective action alternatives and recommendations.

Communicate status to the Steering Committee, Project Sponsor, Project Director and Project Team

Technical Subject Matter Expert

Depending on what technologies are being implemented, ETF may require technical subject matter experts to gain best practice knowledge.  This role should not be confused with a technical project monitor role.  The subject matter expert is to provide best practices.  The monitor is to ensure best practices are being followed.

Functional Project Team Lead

The functional team lead is responsible for defining the business design (and configuration) for all benefit retirement processes and administrative processes associated with benefit administration. The functional team lead is also responsible for leading team members, developing requirements, deliverables, and the testing and training activities.

Technical Project Team Lead

The technical team lead is responsible for the BPS application configuration, modification, data conversion, integration, infrastructure & environment and overall support of the technical environment whether the solution is build or buy.

## F. Conversion Strategy

Please see Appendix E for High Level Conversion Strategy details.

## G. Technical Architecture

If a custom development approach is selected, it is essential to devise a technical architecture that can support both current and future system requirements, yet is streamlined enough that it can be implemented efficiently and with minimal risk.  A key objective is not to repeat mistakes made on the original project, such as designing over-elaborate architectural mechanisms or failing to validate the architecture by using it to implement actual application functionality.

Generally speaking, we believe the basic technology choices made during the original project (Java/J2EE, IBM WebSphere, DB2, etc.) are sound and should be carried forward to the new system.  However, within this broad technology framework we recommend making a number of major architectural changes.  Please note that this section is not intended as a comprehensive architecture proposal; instead, the intent is to identify significant architectural areas for future analysis.  Many of these recommendations are based on established industry trends and proven best practices.

Please see Appendix F for High Level Architecture and Design

# Section IV: Immediate Next Steps

We highly recommend ETF consider the following approach to select its new BPS solution and vendors.

## A. 	Project Charter

ETF should first complete a formal project charter for the RFP project to set the scope and develop the project plan for this activity.  Within this activity, ETF should pay particular attention to defining the scope boundaries it wishes to use when evaluating the package software alternative.  As noted above, ETF should consider a broader scope consisting of Phase 1-7 scope at a minimum when evaluating the package alternative. ETF should also remain open to new ideas that may be presented by package vendors such as solutions they offer to replace related ETF scopes such as the single demographic database for example.  At the same time, ETF needs to control the scope of the package evaluation and focus substantial effort on confirming Phase 1 fit.

ETF should also include the selection of a project monitor within this charter.  The actual project monitor selection process cannot begin until a final package or custom solution is chosen so that the specific skills required by the project can be acquired.

Timeframe:

| Activity | Estimated Hrs. |
| --- | --- |
| 1 |  | Define Business Case | 16 |
| 2 |  | BPS drivers and objectives | 16 |
| 3 |  | Refine scope for each phase of project | 16 |
| 4 |  | Develop project plans | 16 |
| 5 |  | Kickoff project | 8 |
|  |  | Contingency | 30% |
|  |  | Total | 94 |

## B.	RFP

ETF should complete a formal, thorough solution selection process including taking

- Package vendors through detailed demonstration scripts, fit gap analysis, reference checks and final total cost of ownership analysis

- Custom vendors through a series of demonstrations (technical capabilities, prototypes, methodology), reference checks and final total cost of ownership analysis

- Monitoring vendors through detailed demonstrations of methodologies and tools to support their QA/QC activities and reference checks

- The selected vendors through detailed contract negotiations where specific critical skills are secured and any appropriate performance requirements are defined.

ETF’s RFP template ETJ14 ETF Call Management RFP was compared against our best practices and it is an adequate template to use for the BPS RFP process.  The requirements for BPS will need to be defined at a deeper level than the Call Management RFP, but the supporting information and process within that RFP is sufficient to use as a template.

Several key success factors for the RFP process and template include:

- It is not necessary to detail 100% of every scenario for the initial RFP.  Focus on the critical requirements and the flexibility the vendor can provide with their solution.  In addition to the RFP, ETF will have a chance to further define requirements through the vendor conference, demo process, reference site visits, gap analysis, and final vendor negotiation.

- Focus the requirements on ‘what is required’, not ‘how it will work’.  While a part of the RFP should define the technical requirements, avoid defining too many technical constraints that were included in the BPS RFS in 2001.

- Use the existing EDD and Use Cases to support the process, but do not include them as attachments in the RFP.

- Provide adequate time to review the vendor responses, develop the demonstration scripts, vendor time to prepare for the demos, perform gap analysis, perform multiple site visits, and negotiate the contract.

- Provide adequate time to work with the Department of Administration Procurement and Legal offices.

- Develop appropriate weighting criteria.  The Call Center RFP we reviewed weighed Functionality at 34% and Cost at 35%, which is consistent with other organizations, although not a best practice.  ETF must define the correct category weights for the BPS RFP, while considering any DOA mandated requirements.  Based on our experience with other software selections, the following is a guide for approximate major category weights:

  - Functionality:  20%

  - Technical Architecture / Fit:  20%

  - Cost (Initial and Ongoing):  15%

  - Services (Implementation and Support):  15%

  - Viability:  15%

  - Vision:  15%

Timeframe:

| Activity | Estimated Hrs. |
| --- | --- |
| 1 |  | Finalize Requirements | 80 |
| 2 |  | Identify Vendors | 8 |
| 3 |  | Develop and Release RFP | 80 |
| 4 |  | Evaluate Vendor Responses and Select Short List | 80 |
| 5 |  | Prepare for Demonstrations (including developing scripts) | 120 |
| 6 |  | Manage / Conduct Vendor Demonstrations (2 vendors @ 3 days) | 48 |
| 7 |  | Select Finalist | 40 |
| 8 |  | Perform Gap Analysis | 120 |
| 9 |  | Conduct Reference Checks and Site Visits | 40 |
| 10 |  | Negotiate and Sign Contract | 120 |
|  |  | Contingency | 30% |
|  |  | Total | 957 |

Note:  Estimated hours are for core team members, not other functional and technical members that may participate in vendor demos or site visits.

## C.  Skills and Impact Assessment

Once ETF has finalized its solution selection, ETF should also conduct a skills and impact assessment to determine what skills and support structures will be needed to support any new technologies and processes.

## D.  Reengineering

Further, ETF could benefit from conducting re-engineering exercises to identify opportunities currently absent as a result of sustaining a legacy system for a long period of time.

Based on our discussions with ETF, we understand that ETF is planning to complete these immediate next step activities using internal resources.  Therefore, we have not estimated any external costs to support these activities.

# Appendix A:  Post Mortem

# Appendix B:  Revised Implementation Details

Priority Rationale

BPS can be broken down into manageable phases.  The following list of phases provides a high level overview of the scope of each phase and the rationale that was used to create the order of phases.

Phase 1:  Replace Annuity Payment System

- Replace Annuity Payment System, including the payment and reporting of monthly annuitant, disability, and special payments.

- Develop 22 interfaces, including integration with WEBS (RetCalcs and VPS), Single Demographic Database, Reconciliation Tables, import of Wisconsin Vital Statistics and Social Security files, and several other key import / export functions.  (See Interface Estimating Matrix in the appendix for more information)

- Conversion of current Annuity Payment System accounts, payment data, and history.

Rationale:  Replacing the existing Annuity Payment System should be priority one, given the existing limitations, significant manual processes, and support.  The scope should be constrained to the minimum requirements to setup, process, and report benefit payments.  Limit the automation for this phase to the minimum required (Annuity flat file, RetCalcs, Reconciliation, and Demographic Database).  This phase will provide the baseline foundation to build on, scope should be limited, but adequate time and resources are required to put in an effective system.

Dependencies:

- Complete project charter (see section Immediate Next Steps)

- Complete RFP and Solution Selection

- Complete organizational skills assessment (see section Immediate Next Steps)

Risks:

- Limiting the scope and automation to the core benefit payment functionality

Phase 2:  Provide Internet Access and IVR/Call Center Integration to Annuitants

  - Provide secured Internet Access to Annuitants, to view account and payment history, request forms, and update account information online.

  - Provide secured method via IVR/Call Center integration to access account and payment history, request forms, and update account information via the phone.

Rationale:  Providing self-service opportunities to a growing annuitant population will provide a significant payback to ETF.   This was part of the initial vision in 2000.  Based on a study in 2001, over 40% of annuitants surveyed stated they would utilize self-service technologies, thereby reducing call center volume and potential increases in call center and other ETF staffing requirements.

Dependencies:

- Completing phase 1, replacing Annuity Payment System

- Completing Single Demographic Database

Risks:

- Resolving cost component from DOA shared service environment

- Managing organizational change and communication with annuitants to ensure high percentage of use

- Ensure security access controls

Phase 3:  Replace Lump Sum Database

  - Replace Lump Sum Payment system, including the payment and reporting of lump sum payments and rollovers.

  - Automate calculation of Lump Sum benefits, including separations, non-annuitant regular deaths, disability, and special deaths.

  - Develop 7 interfaces, including integration with WEBS (RetCalcs), Single Demographic Database, Reconciliation Tables, and several other key import / export functions.  This phase will re-use many of the interfaces built in phase 1 (See Interface Estimating Matrix in the appendix for more information).

  - Conversion of current Lump Sum accounts, payment data, and history.

Rationale:  Lump sum processes are similar to monthly annuitant, with some variation.  Once the BPS system is in place, lump sum can be converted to BPS and utilize a high percentage of the existing framework, including account setup, payment processing, reporting, and interfaces.

Dependencies:

- Completing phase 1, replacing Annuity Payment System

- Completing Single Demographic Database

Risks:

- None

Phase 4:  Interface with WiSMART

- Interface Accounts Receivable data

- Interface Voucher data

- Process Named Survivor Benefits (Auto Death Processing)

- Process 25% Reduced for Named Beneficiary (Auto Death Processing)

Rationale:  Interfacing with WiSMART will streamline business processes, including death processing, accounts receivable, and financial reporting.  Manual processes using BPS reports can handle these processes in the first phase.  Several automated death benefit processes would be included in this phase.

Dependencies:

- Completing phase 1, replacing Annuity Payment System with integration to WEBS.

Risks:

- Unknown complexity of changes that may be required on WiSMART.

- Unknown complexity of business rules around automated death process.

Phase 5:  Interface with HICS and Replacing Accumulated Sick Leave Conversion System

- Interface with HICS for health insurance data

- Replace ASLCC system

- Automate health insurance eligibility determination

Rationale:  Interfacing with HICS and migrating the functionality of the ASLCC will streamline business processes, including health insurance deductions and reporting.  Manual processes within BPS can handle these processes in the first phase.

Dependencies:

- Completing phase 1, replacing Annuity Payment System

Risks:

- Unknown complexity of changes that may be required within HICS.

- Complexity of business rules to drive integration.

Phase 6:  Integrate Workflow and Imaging within BPS

- Integrate Workflow within BPS (replace Step2000)

- Integrate Imaging within BPS

Rationale:  Workflow and imaging are not essential for benefit payment processing, but rather an enabler for ETF.  Based on the complexity of the business rules, the foundation BPS system and some level of true business process re-engineering should be completed prior to implementing workflow and imaging within BPS.

Dependencies:

- Completing phase 1, replacing Annuity Payment System

- Re-engineering of BPS business processes

- Potential replacement of Step2000 prior to integrating with BPS.

Risks:

- Support issues around Step2000

Phase 7:  Integrate with Duty Disability Database

- Replace Duty Disability Database

- Auto Processing Re-Employed Annuitant

Rationale:  Duty Disability is currently a stand-alone MS Access database used to track 800+ duty disability active accounts and provide data to BPS to process duty disability payments.  The system is stable and provides the functions required to manage duty disability.  The low volume and current stability of duty disability move this to the end of the project list.  However, an interface from duty disability to BPS should be considered in phase 2 or 3 to streamline the data transfer in the interim.  The re-employed annuitant process will be handled manually in phase 1, and has a low impact associated with it trying to automate BPS with WEBS for this function.

Dependencies:

- Completing phase 1, replacing Annuity Payment System

Risks:

- BPS not designed to accommodate duty disability

Other:

Automated Death Benefit:  Automated death benefit processes will be part of several phases.  For example, phase 1 will include automatically stopping payments based on the user entering a date of death.  Future phases will include integration with WiSMART and auto-processing named survivor benefits (phase 4) and automated notification (tied with workflow in phase 6)

Appendix C:  Vendor Profile

# Appendix D:  Detailed Cost Model

# Appendix E:  High Level Conversion Strategy

This provides an overview of the data conversion strategy of the BPS project, including an assessment of the work completed to date and the approach moving forward.

Four main sources of data need to be considered:

- Current Annuity System (phase 1)

- Current Lump Sum Payment System (phase 3)

- Current ASLCC System (phase 5)

- Current Duty Disability System (phase 7)

We estimate 80% of the effort required to analyze and document the source systems has been completed.  Several documents were found under G:\users\bpsaudit\bps\conversion data\clean_up\ related to conversion.  Also, the September 2000 Covansys report, Analysis of the New Payments System Requirements Plan, provides additional detail to conversion requirements.  These documents should be used as a starting point once the solution is selected and the design and development of conversion routines begins.  The time estimated for data conversion during the project will be primarily spent on defining the target system tables and rules, and mapping the source to target.  The target system is likely to have more tables than the source system and may present a risk to the time estimates in the cost model.

A data cleanup effort is ongoing.  We estimate approximately 1000 hours of data cleanup (i.e. see Appendix D, tabs Package Est Model or Custom Est Model, where conversion and cleanup effort are accounted for in separate activities) during the project, regardless of custom or package solution.  If package is selected, the vendor should be able to provide data cleanup tools to assist in any cleanup process.  Sufficient resources should be provided to ensure the data in the new system is clean.

In addition, the ongoing project to implement a single demographic database (DDB) will impact the timing and final approach to converting data to the new BPS system.

Conversion of images from Step2000 has not been reviewed as part of this analysis.

# Appendix F: High Level Architecture and Technical Design

### General Architecture Principles

- Focus on simplicity, rather than designing to cover every possible contingency.

To be effective, an architecture must not only provide critical application services, but must be practical to implement and comprehensible to application developers.  Architectures that are over-generalized or that try to anticipate every possible application scenario typically fail both these tests; it is better to start with an architecture that addresses known requirements, and then extend the architecture as necessary based on feedback from application programmers.

- Assume competent developers will build and maintain the system.

A good technical architecture helps structure applications by providing a consistent set of mechanisms that define the “style” of an application.  However, many architectures fail because they are unnecessarily idiosyncratic, defining one-off solutions to common problems.  This is counter-productive since it prevents developers from using experience they have gained working on other projects.  In particular, the BPS architecture should not try to “shield” application developers from using standard Java/J2EE libraries and programming idioms.  A corollary is that the development team should have a critical mass of experienced developers who have real-world experience building systems using the relevant technologies.

- Focus on the testability of the system.

Because BPS is a large, complex application that will be extended over time, it is critical that the architecture supports building comprehensive suites of automated unit and integration tests.  Without the security provided by automated tests, it is impractical to build the system in a truly incremental fashion.  From a design perspective, it is important that components can be unit tested in isolation, which means that it must be possible to decouple components from the surrounding environment.  For example, it must be possible to test components outside of a full J2EE container, or without requiring that a component be connected to a “live” database engine.

- Make selective use of open source packages.

Over the past several years, there has been a significant increase in the number of high-quality, open source Java code available.  Most of these open source libraries are domain-independent, addressing common problems (such as runtime configuration) found in most enterprise applications.  Where possible, the BPS architecture should leverage available open source frameworks to save development time and reduce risk.  Note that it is important to evaluate open source frameworks as carefully as commercial packages, and use only those frameworks that are of a high technical quality and that have enough “critical mass” to ensure their continued development and support.

### Presentation (Web) Tier Recommendations

- Consider a rich client GUI (instead of a browser client) for dedicated users.

Many J2EE development projects automatically assume that a web (browser-based) client is the best option, typically because of the deployment advantages associated with web-based clients. However, for many business applications this is not the best option.  Rich client GUIs (implemented in Java using the Swing API) are often both faster and cheaper to develop, and provide a superior user experience, especially for power users.  For example, a rich client makes it easier to manage session state or utilize background processing for complex tasks.   Standard tools like Java Web Start can be used to minimize per-client machine configuration and automatically distribute updates when applications are updated.

- Develop web interfaces using Struts or JSF.

If web-based clients are developed, a standard web development framework should be used instead of building a one-off, custom solution.  In the Java space, the two major choices are Apache Struts and JSF.  Struts is the current de facto standard for Java web development, while JSF is a new standard that most (if not all) tools vendors have pledged to support.  Long-term, JSF has a number of technical advantages over Struts, but JSF is a new standard and therefore tools are just starting to emerge.  The decision about which framework to use should be made based on implementation timeframes and current state of JSF tools market.

- Simplify the session management approach.

The original BPS architecture included a very complex “dialog” framework that was overly elaborate for the known application requirements.  A better approach is to manage in-flight transaction state using the standard session management facilities provided by the J2EE container.  Support for multiple open windows and “partitioned” end-user state can layer on top of the basic session facilities if required.

- Use the Business Delegate pattern consistently.

Business Delegate is a standard J2EE design pattern that is designed to reduce the coupling between the presentation tier and remote services.  In essence, this pattern uses a local Java object to prevent the presentation tier from having to interact directly with particular (remote) service implementations.  Among other benefits, consistent use of this patterns helps ensure that the presentation tier can evolve independently of the service tier and that components can be tested separately.

### Business Tier

- Retain an explicit service layer to expose coarse-grained business services.

The purpose of a service layer is to provide applications with a simplified interface to a business transaction, and manage the iterations among multiple business objects that may be required to complete the operation.  While J2EE services are often implemented using Session Beans, this implementation decision should be deferred until more specific requirement emerge; in some cases local objects can be used to implement the service layer as well.

- Develop business objects that have both state and behavior.

A key feature of the original BPS business model was that the domain objects were essentially just data structures, with all behaviors (including simple validations) broken out into separate classes.  Unfortunately, in such a design no real encapsulation of the business objects is possible, and the programming model is less intuitive and harder to test.  Current persistence mechanisms make it possible to implement “feature-rich” business objects that can still be efficiently mapped to persistent storage (see Persistence Tier section).

- Develop a separate mechanism for cross-object business rules.

Even with a rich domain object model, a complex application like BPS requires many business rules that span a range of interrelated objects.  As in the original high-level BPS architecture, we recommend developing a separate facility for implementing and processing such cross-object rules, since often these rules must be invoked from multiple services.  However, it is critical not to over-generalize this feature, and to prototype the proposed design early in the lifecycle to ensure that it can handle realistic application scenarios.

### Persistence Tier

- Use a local persistence API instead of entity beans.

An explicit goal of the original BPS architecture was to leverage all J2EE features, including EJB entity beans.  By contrast, we believe that J2EE features should only be used where they add significant value.  As architects have gained more experience with large-scale J2EE applications, the use of entity beans has decreased dramatically.  It is now far more common to build services that rely on local persistence APIs, since this approach simplifies development (especially rapid/iterative development) and testing.  The forthcoming EJB 3.0 specification is attempting to simplify the use of both session and entity beans, but practical implementations are several years away.

- Use the Data Access Object (DAO) pattern to encapsulate data sources.

The DAO pattern provides a standard, lightweight model for decoupling applications from specific data sources (such as relational databases).  The key feature of this model is that the application interacts with normal Java objects, and used the DAO layer to move objects to and from persistent storage.  As with other several other recommendations, a key benefit of this approach is testability; if also makes it possible to access persistent objects outside a J2EE container environment (for example, for batch programs).

- Leverage a standard O/R mapping framework.

Recently, several robust frameworks have emerged to free developers from having to write low-level JDBC code for database access.  The two most populate options are Hibernate and Java Data Objects (JDO).  Hibernate is an open source framework that is widely used and supported, while JDO is a standard API with numerous available implementations (both commercial and open source).  Of the two, Hibernate is a simpler framework that directly supports the DAO model, while JDO has more features.  Of course, several proprietary O/R mapping tools also exist (including TopLink and CocoBase).  The BPS architecture should standardize on one of these frameworks and use it consistently.

# Appendix G:  Assumptions

| Post Mortem | Six week effort did not allow for in-depth post-mortem analysis. ETF/VK agreed upon high-level reasons for failure and remaining effort spent on the go-forward approach and recommendations |
| --- | --- |
| Revised Implementation | Priority, impact, and effort rationale was based on functional needs and did not take into consideration technical or financial constraints (i.e. Internet capabilities, workflow) Time did not allow for detailed analysis and appreciation for the complexity of system integration points and interfaces (i.e. WiSMART, HICS, RetCalcs, Lump, etc.) Revised implementation strategy scope diagram highlights key system interactions, but may not include all BPS interfaces. |
| Use Cases | Ten of the one hundred seventy use cases were analyzed in detail. Analysis findings were applied to the remaining. Percent completion varies greatly, no consistent percent completion value defined. |
| RFI/Vendor List | Vendor list and compilation of responses are not to be construed for formal RFI process. The exercise was conducted on a limited timeframe to validate market maturity and viable alternatives available to ETF. Vendors identified are not an exhaustive list for potential solution. |
| Architecture | Critique of architecture was derived by the limited documentation available. Confirmed deliverables by interviewing Keith McMillan of nVISIA and Dave Bailey from Covansys. |
| Conversion | Conversion strategy was reviewed by ETF at a high-level to establish phasing dependencies. Detailed evaluation of Single Demographic database did not take place. Data clean-up activities are on-going. 960 hours have been estimated for package/custom phase I. |
| Cost Model Custom/Package | Project Management is 20% total in the estimating model and 25% in planning model. Functional testing is 20% of hours spent between technical design and refinement Cost range variance is -10% and +20% estimated cost Data conversion analysis of source systems is 80% complete. Existing hardware will be used for custom and package. No cost assigned to hardware. Hours were allocated to setup and configuration. Department of Enterprise Technology transaction chargeback remains the same for every solution (legacy/custom/package). Number of user cases, external systems, conversion interfaces, reports, and users is assumed to be within a +/-10% variance. Contingency across entire project is 30% Package business modeling is 50% lower than custom use case/business modeling. Technical documentation and unit testing is included in technical development. Package interface design and development is 50% lower than custom (assume using existing templates). Package report design and development is 50% lower than custom. Transition activities for phase 2 (Internet and IVR) is at 10% of total phase in hours. Project manager assumes 1.5:2 ratio of ETF:Vendor Project monitor estimates are included in the Project Monitor Role sheet of the cost model in Appendix D. Total cost based on current phased plan. Does not take into consideration legislative changes or alternate vision. |

# Footnotes

Viability considers the financial strength of the organization, maturity, and market longevity.

Vision takes into consideration the organizational commitment towards the product and/or services.

# Text boxes

Prepared by

115 South 84th Street

Milwaukee, WI  53214

414-777-5500

www.virchowkrause.com